## Sheet1
Project Master Schedule
| 2018-01-14 | 2018-01-21 | 2018-01-28 | 2018-02-04 | 2018-02-11 | 2018-02-18 | 2018-02-25 | 2018-03-04 | 2018-03-11 | 2018-03-18 | 2018-03-25 | 2018-04-01 | 2018-04-08 | 2018-04-15 | 2018-04-22 | 2018-04-29 | 2018-05-06 | 2018-05-13 | 2018-05-20
Planning | bar: 2018-01-14 to 2018-01-21
Research | bar: 2018-01-14 to 2018-03-04
Design | bar: 2018-02-11 to 2018-04-08
Implementation | bar: 2018-03-18 to 2018-04-22
Follow Up
Schedule Breakdowns
| 2018-01-14 | 2018-01-21 | 2018-01-28 | 2018-02-04 | 2018-02-11 | 2018-02-18 | 2018-02-25 | 2018-03-04 | 2018-03-11 | 2018-03-18 | 2018-03-25 | 2018-04-01 | 2018-04-08 | 2018-04-15 | 2018-04-22 | 2018-04-29 | 2018-05-06 | 2018-05-13 | 2018-05-20
Planning
Contact with Client
Research
Create Scope
Design Mock Database
Design Mock GUIs
Design Flow
Create UML Diagram
Design Test Cases
Design
Create Tables
Create Data Classes
Create GUIs
Create Queries
Basic Application Functionality
Connect Application to DB
Run Test Cases
Implementation
Push to Client
Client Training
Monitored Trial
Debugging and Redesign
Follow Up
Meet with Client
Full Launch